## MIS
Sr | case_id | Month | Start_Date | Team | Title | Description | Status | Benefit | Remark | End_Date | result | R1
1 | Case_Id01 | Jan | 2027-01-12 | Zubin, Sonal | Incoming Mail | Define process flow based on use cases | done | Track incoming emails by inquiry, escalation, and approval categories | design & developed | 2026-01-19 | achieved
2 | Case_Id01 | Jan | 2026-01-20 | Zubin, Sonal | Outgoing Mail | Design workflow for outgoing emails | done | Track both incoming and outgoing emails in a single SharePoint using NLP-based segregation | design & developed | 2026-01-21 | achieved
3 | Case_Id01 | Jan | 2026-01-21 | Zubin, Sonal | Incoming + Outgoing | Design workflow for incoming and outgoing emails | done | Track the incoming & outgoing in the same sahrepoint, NLP based approach segregation | design & developed | 2026-01-23 | achieved
4 | Case_Id01 | Feb | 2026-02-25 | Zubin, Lilac | Incoming + Outgoing | Create TAT-based unread email reader with deadline alerts | done | Implement deadline tracking to avoid delays | design & developed | 2026-02-03 | achieved
5 | Case_Id02 | Feb | 2026-02-12 | Lydia | Talent_Hub | Implement and document Print Layout features | done | Monitor completed course learning and generate a properly formatted final summary | design & developed | 2026-02-12 | achieved
6 | Case_Id03 | Feb | 2026-02-23 | Lydia | Form | Integrate multiple forms into one system | done | Use branching logic (one-to-many workflow approach) | design & developed | 2026-02-22 | achieved
7 | Case_Id04 | Feb | 2026-02-16 | Zubin | IET | Establish data protection and anti-manipulation controls | done | Capture user data automatically, compile it for analysis, and send via email | design & developed | 2026-03-02 | De-Active
8 | Case_Id33 | Feb | 2026-02-23 | Zubin, Lilac | PNR Stats Model | Develop a clone version of PNR Stats | done | Track PNR count and duration | design & developed | 2026-04-02 | achieved | shared final copy with head for test
9 | - | Feb | 2026-02-23 | Zubin,Lilac, Arti | Mandar's file | Design process to consolidate all file data into a single file | done | Consolidate all information into a single file to save time | design & developed | 2026-03-04 | De-Active
10 | Case_Id10 | Feb | 2026-02-24 | Sonal, Shruti, Nilufer, Murillo | Myfare Pass-on Entry | Enable data transfer from Myfares 1.0 / Myfares 2.0 to Excel | done | Eliminate manual data entry from SharePoint to Excel | design & developed | 2026-03-06 | achieved | entries only coming wrong then issue
11 | Case_Id05 | Feb | 2026-02-25 | Sonal | Reminder Mail | Design the Auto-Reminder | done | Sent the reminder to team on weekly basis | design & developed | 2026-02-02 | achieved
12 | Case_Id08 | Mar | 2026-03-02 | Vinod | Attendance Autofiller | Design the Autofiller from One Excel to Another Excel | done | Capture the Data from from one excel and deploy it in to another | design & developed | 2026-03-09 | achieved
13 | - | Mar | 2026-03-02 | Lydia | Automation of Post-Training Feedback Forms | Automation of Post‑Training Feedback Forms: To automate the sending of feedback forms to employees upon training completion. | done | Enables timely and consistent collection of training feedback; Reduces manual effort in sending feedback forms; Ensures a standardized post‑training feedback process | design & developed | 2026-03-06 | achieved
14 | Case_Id06 | Mar | 2026-03-02 | Lydia | Automation of Onboarding Training Instructions | Automate the sending of the new joiner welcome email so it is triggered automatically and delivered to every employee on their date of joining. | done | Professional and seamless onboarding experience for all new joiners | design & developed | 2026-03-09 | achieved
15 | Case_Id08 | Mar | 2026-03-02 | Akbar, Michael | RT WFH file | Automate to avoid error and reduce time of compile and multiple entry at the same time | done | Reduce the timely process of download, compile, data entry | design & developed | 2026-03-10 | achieved
16 | Case_Id07 | Mar | 2026-03-13 | Lydia | Automation of Onboarding Training Completion and Closure | Automatically update onboarding training status in Microsoft Lists and trigger a closure email once a new joiner submits the training completion MS Form. | done | Eliminates manual tracking and follow-ups while streamlining the onboarding process. | design & developed | 2026-03-20 | achieved
17 | Case_Id12 | Mar | 2026-03-18 | brayan | Macros : Telex Data Extraction for Cancelled flights during major Disruptions | Automation of telex review and data generation process. | done | Saves 10-12 hours for 100 flights, reduces errors, boosts productivity, and enables faster decision-making. | design & developed | 2026-03-23 | achieved
18 | - | Mar | 2026-03-20 | Lydia | Automate culture snippet emails | Store culture snippets in a Microsoft List, manage order, and auto-send Fridays 10 AM via Power Automate, marking each as Sent. | done | Ensures consistent weekly delivery, no manual effort, and easy planning in advance. | design & developed | 2026-03-20 | achieved | recommend the feature of schedule mail using outlook
19 | - | Mar | 2026-03-12 | Sonal | Training Session Recording App | Create an in-house app to record and upload training sessions, avoiding repetition and enabling wider audience training. | done | Provides reusable training content, though recording and uploading may be challenging. | New Entry | 2026-03-12 | achieved | recommed the feature of ms one note issue of storing
20 | Case_Id13 | Mar | 2026-03-23 | Neha | LWP Data Collection & Payroll Automation | Automates the collection, consolidation, and reporting of Leave Without Pay (LWP) data from supervisors to HR and Finance using Microsoft 365 tools. | done | Reduces manual effort and errors, saves 6–8 hours monthly, and ensures accurate, centralized payroll data processing. | design & developed | 2026-03-24 | achieved | devloped and run successfully but diverted to spine
21 | Case_Id16 | Apr | 2026-04-03 | Lydia | Automated Mandatory Training Compliance Tracker(Recertification) using Excel Logic | Centralized Microsoft Lists tracker enables supervisors manage training compliance automatically | done | Reduces manual effort ensures timely compliance visibility and clear ownership | design & developed | 2026-07-13 | achieved
22 | Case_Id14 | Apr | 2026-04-08 | Lydia | Quarter_Excel Automation_Multiple Access_Dept wise_Overall Summ of Trng Man Hr | Automates reminders, updates tracking, confirmations, and final approval communication workflow | done | Ensures timely updates, reduces follow-ups, improves visibility, centralized tracking system | design & developed | 2026-04-21 | achieved
23 | Case_Id15 | Apr | 2026-04-09 | Lydia | Automated Training Quiz Scoring, Reporting and Email Distribution System | Automates quiz scoring, consolidation, reporting, and stakeholder email communication workflow | done | Reduces manual work, improves accuracy, saves time, faster reporting visibility | design & developed | 2026-04-09 | achieved | came up with Version 2 approach to respective team wise resulting : 6/10/2026
24 | Case_Id18 | Apr | 2026-04-16 | Mitra, rajesh | SPINE Annual Leave Calculation for Audit | SPINE Annual Leave Calculation for Audit. | done | This automation streamlines data processes by eliminating manual work, reducing errors, ensuring consistent reporting, and saving time for HR, Operations, and Finance teams. | design & developed | 2026-04-16 | achieved | Excel Online format shared to rajesh Alternative can be achieved using spine via uploading the csv file
25 | Case_Id33 | Apr | 2026-04-17 | Taruna | Automation of details entered in the Quality check file | Automate capture of RLOC details and user details into one final, consolidated file. | done | Time per employee entry will be reduced as most details are auto-captured or selected via dropdowns, with minimal manual input required for specific system-based fields like RLOC for queues. | design & developed | 2026-06-19 | achieved
26 | Case_Id20 | Apr | 2026-04-21 | Sonal | Automation Idea Submission Notification via Microsoft Forms and Teams | Automatically posts new automation ideas from Forms directly to Teams | done | Ensures instant visibility faster review and no missed automation ideas | design & developed | 2026-04-21 | achieved
27 | Case_Id21 | Apr | 2026-04-24 | Lydia | Centralized Contact Repository Automated Using SharePoint And Power Automate | Automatically synchronize contacts between SharePoint lists ensuring complete, consistent information | done | Eliminates duplication, improves accuracy, enables real time centralized contact management | design & developed | 2026-04-24 | achieved
28 | Case_Id22 | Apr | 2026-04-16 | Lydia | Training Compliance Visibility Through Automated Tracking Framework | Automates training tracking and presents due status through centralized summaries. | done | Improves transparency, enables proactive planning, ensures consistent training coverage. | design & developed | 2026-04-28 | achieved
29 | Case_Id23 | Apr | 2026-04-21 | Lydia | Mail Compiler for section Based in one book | Automate saving sent emails into OneNote sections based on subjects | done | Centralized searchable archive eliminates manual effort and improves future reference | design & developed | 2026-04-29 | achieved
30 | Case_Id24 | Apr | 2026-04-22 | Vinod | Monthly Fare Report Consolidation | Consolidate seven team reports into one centralized monthly master workbook. | done | Eliminates manual consolidation, saves time, improves reporting accuracy significantly. | design & developed | 2026-05-06 | achieved
31 | - | Apr | 2026-04-22 | Vinod, Sonal | Copilot Awarness Flow Structuring using Power Automate flow design | Automatically sent mail to user on specific day at specific time | done | Minimize the repetative task and increase productivity | design & developed | 2026-04-22 | achieved
32 | - | Apr | 2026-04-23 | Lydia | Schedule Mail Feature Usage | Schedule a mail using Scheduler feature | done | Draft it and keep it schedule to be sent on set duration | design & developed | 2026-04-23 | achieved
33 | Case_Id25 | Apr | 2026-04-26 | Neha | Automated new joiner check-in emails streamline HR follow-up communication processes | System automatically triggers standardized check-in emails based on employee joining dates | done | Improves efficiency, ensures timely follow-ups, reduces missed employee check-ins consistently | design & developed | 2026-05-08 | achieved
34 | Case_Id26 | May | 2026-05-07 | Lydia | End-to-End Business Process Automation Implementation | Automates workflow, reduces manual tasks, ensures seamless system integration | done | Improves efficiency reduces errors increases productivity through automated workflow execution | design & developed | 2026-05-21 | achieved
35 | Case_Id27 | May | 2026-05-21 | Shruti | Automation of MoM (Minutes of Meeting) Acknowledgement Tracking – Fares Team | Automates MoM acknowledgment tracking, standardizes data, and generates structured reports. | done | Eliminates effort ensures accuracy improves visibility enables reporting scalability benefits | design & developed | 2026-05-22 | achieved
36 | Case_Id28 | May | 2026-05-26 | Murillo | Automate Monthly 1A Login Verification Using Forms and Power Automate | Collect monthly login confirmations and screenshots through automated forms workflow. | done | Ensures active 1A access, reduces renewal costs, improves compliance. | design & developed | 2026-06-03 | achieved
37 | Case_Id29 | Jun | 2026-06-10 | Rajesh | Email Mail Merge for Asia Miles Adjustment Notification | Automates sending personalized Asia Miles adjustment emails from Excel data with dynamic formatting and shared mailbox integration | done | Saves time, reduces manual errors, and ensures consistent, accurate communication at scale. | design & developed | 2026-06-10 | achieved
38 | Case_Id30 | Jun | 2026-06-02 | Rajesh | Automated Email Tracking and SLA Monitoring System for Shared Mailbox | Captures incoming outgoing emails timestamps updates status enables SLA reporting | done | Improves response visibility reduces delays ensures accountability enhances operational efficiency | design & developed | 2026-06-04 | achieved
39 | - | Jun | 2026-06-02 | Chandrashekhar | Automated Incoming Mail Tracker for Efficient Document Receipt Management | Automatically captures, tracks, and organizes incoming mails and documents. | done | Reduces manual effort, improves visibility, accuracy, and response times. | design & developed | 2026-06-02 | achieved
40 | - | Jun | 2026-06-11 | Pravin | Automated Incoming Mail Tracker for Efficient Document Receipt Management | Automatically captures, tracks, and organizes incoming mails and documents. | done | Reduces manual effort, improves visibility, accuracy, and response times. | design & developed | 2026-06-11 | achieved
41 | Case_Id31 | Apr | 2026-04-15 | Mitra, rajesh | Automated sorting of the Monthly Booking List (MBL) before handling. | Automated sorting of Monthly Booking List improves efficiency and accuracy | done | Improves efficiency and reduces manual effort by automating MBL sorting, enabling faster processing, standardized handling, and lower risk of errors. | design & developed | 2026-04-21 | achieved
42 | Case_Id32 | Jun | 2026-06-16 | Sonal | Automated Training Completion Tracking and Reminder System | Automates training tracking, updates completion status, and sends reminders. | done | Saves time, improves accuracy, ensures compliance, reduces manual effort. | design & developed | 2026-06-16 | achieved
43 | Case_Id33 | Jun | 2026-06-16 | Zubin, Lilac, Shikha, Taruna | PNR-based timer automation for efficient activity tracking and reporting system | Automates start end timing captures PNR data validates inputs accurately | done | Reduces manual errors improves accuracy saves time ensures reliable tracking | design & developed | 2026-06-19 | achieved
44 | Case_Id34 | Jun | 2026-06-29 | Neha | Automated Medical Insurance Approval Workflow for Employee Confirmation Management System | Monthly system identifies employees due and sends supervisor approval emails | done | Reduces manual effort ensures timely decisions improves tracking and accuracy | design & developed | 2026-06-29 | achieved

## Automation_Mng
|  | Backup | Status
Case_Id | Title | 35
Case_Id01 | Incoming + Outgoing Mail Tracker | 1 | +++
Case_Id02 | Talent Hub course completion summary | 1 | +++
Case_Id03 | Form Branching technique | 1 | +++
Case_Id04 | IET time stamp | 1 | ----
Case_Id05 | Reminder Mail of Automation feedback on weekly basis | 1 | +++
Case_Id06 | Onboarding Training Instruction | 1 | +++
Case_Id07 | Onboarding Training Closure mail | 1
Case_Id08 | RT WFH file sync & compile | 1 | +++
Case_Id09 | PNR Tracker officeid, que wise | 1 | +++
Case_Id10 | Myweekly Report from Myfares 1.0 | 1 | +++
Case_Id11 | Login & Logout for WFH | 1 | +++
Case_Id12 | Talax CNL's one Tracking | 1 | +++
Case_Id13 | LWP Data Collection & Payroll Automation | 1 | +++
Case_Id14 | Quarter_Excel Automation_Multiple Access_Dept wise_Overall Summ of Trng Man Hr | 1 | +++
Case_Id15 | Automated Training Quiz Scoring, Reporting and Email Distribution System | 1 | +++
Case_Id16 | Automated Mandatory Training Compliance Tracker(recertification) using Excel Logic | 1 | +++
Case_Id17 | Automatically update the form responses in the training tracker using Power automate | 1 | +++
Case_Id18 | SPINE Annual Leave Calculation for Audit | 1 | +++ | implemented using excel online & Alternative can be achieved using spine
Case_Id19 = Case_Id33 | recieved and looks same as Case_Id33 wrapped up in same App | 1 | +++
Case_Id20 | Automation Idea Submission Notification via Microsoft Forms and Teams | 1 | +++
Case_Id21 | Centralized Contact Repository Automated Using SharePoint And Power Automate | 1 | +++
Case_Id22 | Training Compliance Visibility Through Automated Tracking Framework | 1 | +++
Case_Id23 | Mail Compiler for section Based in one book | 1 | +++
Case_Id24 | Data Compiler in one and share it with AM via Mail | 1 | +++
Case_Id25 | Checkin Mail Trigger New Joinee | 1 | +++
Case_Id26 | 100 Days Past In-house Training Mail to the Supervisor | 1 | +++
Case_Id27 | Automation of MoM (Minutes of Meeting) Acknowledgement Tracking – Fares Team | 1 | +++
Case_Id28 | Murillo Summerizer Amadeus Login based | 1 | +++
Case_Id29 | Email Mail Merge for Asia Miles Adjustment Notification | 1 | +++
Case_Id30 | Automated Email Tracking and SLA Monitoring System for Shared Mailbox | 1 | +++
Case_Id31 | Automated sorting of the Monthly Booking List (MBL) before handling. | 1 | +++
Case_Id32 | Automated Training Completion Tracking and Reminder System_"Yes"(sonal) | 1 | +++
Case_Id33 | PNR-based timer automation for efficient activity tracking and reporting system | 1 | +++
Case_Id33 | Automation of details entered in the Quality check file | 1 | +++
Case_Id34 | Automated Medical Insurance Approval Workflow for Employee Confirmation Management System | 1

## Time_Saving
Dept_Req. | Impl. Year | Impl. Month | Process | Automation | Details | Hours Saved | Remarks
Training_Lydia | 2026 | February | Manually sending feedback emails to employees once a training session is completed. | Automation of Training Feedback Forms :The automation streamlines the training feedback process by automatically sending feedback emails to employees once a training session is completed. | Automation of Post‑Training Feedback Forms: To automate the sending of feedback forms to employees upon training completion. | Approx 14hrs/Month | 14 hr 00 min
Training_Lydia | 2026 | February | Manually Sending Onboarding Training Instruction to the new joiner. | Automation of Onboarding Training Instruction: Automate the sending of the new joiner welcome email so it is triggered automatically and delivered to every employee on their date of joining. | Automate the sending of the new joiner welcome email so it is triggered automatically and delivered to every employee on their date of joining. | 2hrs/cycle | 8 hr 39 min
Fares_Sonal | 2026 | February | Manual drafting and sending reminder emails weekly without automation support | Automated weekly reminder emails scheduled using Power Automate without intervention | Saves time ensures consistency reduces dependency and improves communication efficiency | 10 min/week | 0 hr 43 min
Fares_Sonal | 2026 | February | Manual data collection from systems and entering into Excel weekly | Automated data transfer from Myfares system directly into Excel sheet | Reduces manual entry saves time improves accuracy minimizes data errors | 20min/day | 7 hr 20 min
Training_Lydia | 2026 | March | Onboarding Training - Closure: Automate an email to the new joiner marking the closure of his/her onboarding training. | Automation of Onboarding Training Completion and Closure | Automatically update onboarding training status in Microsoft Lists and trigger a closure email once a new joiner submits the training completion MS Form. | 15mins/cycle | 1 hr 04 min
Training_Lydia | 2026 | March | Culture snippets are currently drafted and sent manually every Friday at 10:00 am via email. The activity is fully dependent on manual effort and requires that I am available at the scheduled time. | Automate culture snippet emails | Store culture snippets & manage order, and auto-send Fridays 10 AM | 15mins/cycle | 1 hr 04 min
HR_Neha | 2026 | April | Currently, 1‑month and 3‑month check‑in communications for new joiners are shared manually by the HR team via email. This process is proposed to be automated. Upon completion of 1 month of an employee’s tenure, an automated email will be triggered by HR to the respective Supervisor, Department Head, and HR Head. | Automated new joiner check-in emails streamline HR follow-up communication processes | System automatically triggers standardized check-in emails based on employee joining dates to the Superviosr & Assitant Manager | 10 min / per employee | 7 hr 50 min
Training_Lydia | 2026 | April | Supervisors updated training details in separate offline files.Files were downloaded, edited, and emailed back to Training Team.Multiple follow‑ups were required to track pending updates.Data had to be manually consolidated. | Quarter_Excel Automation_Multiple Access_Dept wise_Overall Summ of Trng Man Hr | Automates reminders, updates tracking, confirmations, and final approval communication workflow | 14hrs saved per quarter | 4 hr 40 min
Training_Lydia | 2026 | April | Quizzes are shared via MS Forms, however marking, result consolidation, and report sharing are still done manually | Automated Training Quiz Scoring, Reporting and Email Distribution System | Automates quiz scoring, consolidation, reporting, and stakeholder email communication workflow | 7 hours per quiz for 300 participants | 7 hr 00 min
Training_Lydia | 2026 | April | Culture Though For Today, Copilot@Work, and Auto Mate Corner emails remain in my Sent Items.Referring to older emails requires manual search in Outlook. | Mail Compiler for section Based in one book | Automate saving sent emails into OneNote sections based on subjects | 10mins | 1 hr 26 min
Fares_Vinod | 2026 | April | To maintain the data occupancy and other fare filing related data, multiple files are maintained. | Monthly Fare Report Consolidation | Consolidate seven team reports into one centralized monthly master workbook. | 4.5 Hours | 4 hr 30 min
Training_Lydia | 2026 | April | There is no system-driven check on who last attended training or who is due, No fixed training frequency (e.g., every 60 days) is enforced per individual, Training tracking and follow-ups are manual | End-to-End Business Process Automation Implementation | Automates workflow, reduces manual tasks, ensures seamless system integration | 24 hours per month for 13 departments | 24 hr 00 min
Training_Lydia | 2026 | April | Manually managed contact repository using Excel spreadsheets and email communications. | Automatically synchronize contacts between SharePoint lists ensuring complete, consistent information about active & Deactive Id | Automatically synchronize contacts between SharePoint lists ensuring complete, consistent information | 10 min | 3 hr 40 min
Fares_Sonal | 2026 | April | Manual checking Forms and posting ideas to Teams channel manually | Automation Idea Submission Notification via Microsoft Forms and Teams | Automatically posts new automation ideas from Forms directly to Teams | 10 min/week | 0 hr 43 min
Fares_Vinod | 2026 | April | Manual drafting and sending emails weekly required user effort every time | Using Power Automat Flow Structuringe flow design for Copilot Awarness | Automatically sent mail to user on specific day at specific time | 10 min/week | 0 hr 43 min
Training_Lydia | 2026 | April | Manual tracking of training compliance and recertification across teams individually | Automated Mandatory Training Compliance Tracker(Recertification) | Centralized Microsoft Lists tracker enables supervisors manage talent Hub training compliance automatically | 2.15hrs/cycle | 2 hr 09 min
FOP_NCT_Mitra | 2026 | May | Monthly Booking List (MBL) received for crew positioning was earlier manually rearranged by date, region, and priority before processing. | Automated sorting of the Monthly Booking List (MBL) before handling. | Automated MBL sorting removed manual effort, improved consistency and speed | 1.15 Hours | 1 hr 09 min
Fares_Sruthi | 2026 | May | Manual tracking of form responses and identifying non respondents after deadline | Automates acknowledgment tracking generates reports highlights pending responses without manual effort | Eliminates manual effort improves accuracy ensures visibility enables structured reporting scalability | 2.5 Hours | 2 hr 30 min
Fares_Murillo | 2026 | May | Manual monthly email tracking and collecting screenshots from team members | Automated monthly reminders collect responses and screenshots without manual follow ups | Ensures compliance reduces effort improves tracking prevents access issues costs | 2.5 Hours | 2 hr 30 min
IET_Dusa | 2026 | June | Manual tracking of emails timestamps updating status and monitoring SLA | Automates email tracking timestamps updates status and monitors SLA performance | Improves visibility reduces delays ensures accountability enhances overall operational efficiency | 5 Hours (depends on email volume) | 5 hr 00 min
ACQ_Muriel | 2026 | June | Manual email creation copying data and sending messages individually | Automates mail merge sending personalized emails from Excel dynamically | Saves time reduces errors ensures consistency enables large scale communication | 1min/mail | 13 hr 20 min
Training_Sonal | 2026 | June | Tracking training completion status and managing reminders for pending employees | Automated form integration updates status and triggers reminder emails instantly | Enhances efficiency, reduces errors, ensures compliance and improves operational productivity | 6 times/month | 2 hr 36 min
QC_Lilac,Taruna,Zubin | 2026 | June | Manual PNR-based task tracking with time capture and duration calculation | PNR timer automation replacing manual tracking and improving operational efficiency | Captures activity duration automatically eliminating manual logging and calculation efforts | 27 hours/month | 27 hr 00 min
HR_Neha | 2026 | June | Manual tracking emails follow-ups delays approvals lack transparency high effort inefficient | Automated Medical Insurance Approval Workflow for Employee Confirmation Management System | Monthly system identifies employees due and sends supervisor approval emails |  | 15 hr 00 min
Training_Lydia | 2026 | July | Manually tracked employee recertifications using spreadsheets emails and follow-ups | Automated monthly training compliance tracking and supervisor notification process | Centralized tracker sends reminders ensuring timely training completion compliance | 2.15hrs/cycle | 2 hr 15 min